## Admin View
QSOFT VIETNAM CORPORATION Add: Nbr8 No3 Dich Vong Urban Areas, Cau Giay Dist, Ha Noi, Viet Nam Tel: 84-43-792 5148 Fax: 84-43-792 5147 Email: contact@qsoftvietnam.com Website: http://www.qsoftvietnam.com | [5 empty] | Code: 03e_BM_SA_KD/QSOFT_v1.0 Effective date: 1-Jan-17 Version: v1.0
EFFORT BREAKDOWN AND COST ESTIMATION
Project:
Created by:
Effective:
Validation time: 45 days
Features | Acceptance Criteria | Estimation |  |  | Total Effort | Unit Price | Amount
|  | Requirement Development | Implementation | Testing | Man-hours
Project initiation | Project environment setup | [5 empty] | 0
- Project planning (PM) | Create project plan | [5 empty] | 0
- Technical Solutioning (TO) | Create Implementation plan & Apply system architecture, starter kit, technical training | [5 empty] | 0
Design
Design | … | [5 empty] | 0
Software development (PO, DEV) | [6 empty] | 0
I. Course management | [6 empty] | 0
1. Course list | Implement the following improvements + Course list order (anphabet instead of created time) + Search/ Filter: Course code, Creator, Created date, Status, Library (Field of the course); + Columns to show: Check box for bulk action; image, Course ID, Course name; Created date; Creator; Duration; Module; Library; Action (View detail; Clone, Edit, Delete, Change status, Published - Unpublished course), duration; Status (Publish/Draft); request numbers + Number of participants ==> progress of participants + Course progress + Scoring/ mark management + Edit course/Clone/Del/ assign course/ Publish - unpublish course + Share course via social media or get the course's link + Button Export csv | 5 | 22 | 5 | 32 |  | 0
| Export course: Fields as same as import course | 0.5 | 6 | 2 | 8.5 |  | 0
1.1. Import Course list | Import course list | 1 | 13 | 2 | 16 |  | 0
2. Create course |  |  |  |  | 0 |  | 0
2.1. Course info (improvement) | Improve 1. Course information '+ Course title, Course description, Course ID - System autogenerates, Image, Author; + Course type (Self-study; virtual classroom; real classroom - sit limit, date, time, room; activity - workshop, exercise, questionair): optional + Course level (Basic, Medium, Advanced): optional + Require level for trainee: Optional + Libraries: ??? + Skill achieved after finish/ course tags: optional 2. COURSE COMPETION SETTINGS + Course duration: required + Days allowed to complete + Allow retake ==> Retake after xxx months, + Allow certificate, + Allow review & rating + Public course or not 3. Exam Show all fields available in stead of selecting the exam attempts + Required field, Optional field, Instruction & warning message + Update course ==> recalculate trainee result? send noti to trainee 4. UI, UX '- Show signals of required fields - Validation for single field - Message content and position | 2 | 12 | 4 | 18 |  | 0
3. Course Details |  |  |  |  | 0 |  | 0
Course information | Re-organize the information to be more user friendly | 2 | 5 | 2 | 9 |  | 0
3.1. Assign course to trainee (Rework) | Assign course to: + Individual + Groups of trainees/ departments + Group of trainees/Departments, excluding someone Functions: - Assign trainee by email or username - Assign role of trainee in the course --------------------- + Assign title; Assign description, Assign ID, Assingor; + Users: paging, Filter and search function by job title, department, approved + Assign to single user/ group; + Assign department, including members in that departments + Assign one department or more than one department + Assign Department with function to exclude members if needed + Assign roles to users for the course + Attendance rate and reason log + Required field, Optional field, Instruction & warning message | 4 | 12 | 4 | 20 |  | 0
Course request from user | Course request from user: Accept, Reject, Onhold, Del | 4 | 6 | 1 | 11 |  | 0
3.1.2. User list | - Users list - Search - Filter - Status of attendance confirmation: status with reason - Del users from course | 2 | 18 | 3 | 23 |  | 0
3.2. Course Module (Improvement) |  |  |  |  | 0 |  | 0
3.2.1 Module list (Improve) | - Module list: + Module list order (anphabet instead of created time) + Module code, Module name, Module description, Creator, Created date, Status, Document; + Rearrange module/ Edit/ Clone/ Del/ Published - Unpublished + Export csv | 1 | 21 | 2 | 24 |  | 0
3.2.2. Add new module (improve) | - Add/ Import new module: + Module title, Module description, Image + Add content: Upload, Create new or choose from Library + Public module or not + Required % finish before move to next module + Required field, Optional field, Instruction & warning message | 1 | 12 | 2 | 15 |  | 0
3.2.3. Document Manager (new) for each individual module | - Documents for module: Size of documents, video type??? - Reference documents ==> VIew document? Search (free text) | 3 | 12 | 2 | 17 |  | 0
3.3.3. Exam Management (new) For each individual module | - Exam list: + Exam title, Total question, Exam duration, Exam total mark, Passing % + Edit/ clone/ del/ publish - unpublished + Export csv - Add/ import new exam: + Exam type: Multiple choice, Freetext, Info page (include image), Upload output + Exam title, question content, description, duration to attempt question, question mark, reference (image, video, audio, etc) + Answer option (1 - n), Correct answer + Add more question + Duration to take exam, Exam total mark, Passing % + Allow exam attempt (xxx times) + Public exam or not + Required field, Optional field, Instruction & warning message ==> valiation when create course (number of question, number of attempts, exam version for each retake exam?) ==> Key management for exam | 5 | 31 | 5 | 41 |  | 0
3.3.4. Course quiz | - Quiz list: + Quiz list order: follow quiz arrangement + Quiz number, Quiz content, Quiz duration, question mark, answer option, correct answer + Rearrange question/ edit/ clone/ del/ publish - unpublished + Export csv - Add/ import new quiz: + Quiz type: Multiple choice, Freetext, Info page (include image), Upload output + Question content, description, duration to attempt, question mark, reference (image, video, audio, etc) + Answer option, Correct answer, Passing % + Add more question + Public question or not + Required field, Optional field, Instruction & warning message | 4 | 22 | 5 | 31 |  | 0
4. Document Manager for the whole course | - Documents for module: Size of documents, video type??? - Reference documents - Filter (Module), Search | 4 | 6 | 2 | 12 |  | 0
5. Exam Management for the whole course | - Exam list: + Exam title, Total question, Exam duration, Exam total mark, Passing % + Edit/ clone/ del/ publish - unpublished + Export csv - Add/ import new exam: + Exam type: Multiple choice, Freetext, Info page (include image), Upload output + Exam title, question content, description, duration to attempt question, question mark, reference (image, video, audio, etc) + Answer option (1 - n), Correct answer + Add more question + Duration to take exam, Exam total mark, Passing % + Allow exam attempt (xxx times) + Public exam or not + Required field, Optional field, Instruction & warning message | 4 | 22 | 5 | 31 | 103.5 | 3208.5
Certi management | List, upload, edit, add, del | 3 | 15 | 2 | 20 |  | 0
6. Request Management | Requester info: Name, ID, Department/ Division, Job title, Request time Action: Accept; Reject, Onhold; Reason for reject & holdon Update status of request Request updated | 4 | 6 | 2 | 12 |  | 0
7. Course final list | Course Final list Course Progress of the list ==> List users who already joined course | 3 | 3 | 1 | 7 |  | 0
8. Clone (fix) | Problems as create the course | 1 | 5 | 1 | 7 |  | 0
9. Edit the course | Problems as create the course | 1 | 5 | 1 | 7 |  | 0
10. Import/ Export the course | Fix bugs | 1 | 15 | 1 | 17 |  | 0
11. Run Report | Need more define | 8 | 12 | 1 | 21 |  | 0
II. Users Managments | Users managers Roles Managers Permission manager |  |  |  | 0 |  | 0
1. Create users | - Create users with password and profile information - Assign roles for users | 2 | 15 | 1 | 18 |  | 0
2. Users list | - List of all users will roles - Can sort filter by alphabet - Can search user name by keywords - Can filter user by department, users roles | 1 | 15 | 1 | 17 |  | 0
3. Edit user information | - edit above information | 1 | 6 | 1 | 8 |  | 0
4. Change password | - Change password for users - User send email change password - System send email with new password to users - User use new password to reset password | 0.5 | 4 | 0.5 | 5 |  | 0
5. Profile (Improve) | - Personal info: Image (upload): optional, fullname (edit): required, username (edit + alert unique): required, user ID (show), Change password (Recent pass, new pass, re-enter new pass, forget password???) - Address info: + Hired date (choose date): optional, Location: dropdown list: required, Division: dropdown list: required, Business unit: required + Phone: required, fax: optional, skype: optional, email: required, address: optional - Noti setting: + Receive method: instant mess, email + Content: Course: assigned, un-assigned, approve request: new, reject request: new + Account change: password changed, assigned new role: new | 1 | 5 | 1 | 7 |  | 0
6. Import the list of users | - Import the list of users with defined fields | 1 | 12 | 2 | 15 |  | 0
V. Roles Management |  |  |  |  | 0 |  | 0
1. Add/edit/delete the roles | Add/edit/delete the roles Role name Role type | 1 | 10 | 1 | 12 |  | 0
2. Roles list | List of all roles created Search, sort Can add/edit/delete the roles | 1 | 10 | 1 | 12 |  | 0
3. Roles permission | - Select roles or set of roles - Set permission: Full permission or custom permission + Custom permission: Select module, select action to those modules ==> Check box options (dev: recheck where setted up role in code) | 8 | 50 | 30 | 88 |  | 0
III. Department Management |  |  |  |  | 0 |  | 0
1. Location |  |  |  |  | 0 |  | 0
1.1. Location list (Improve) | - Location order: Location name anphabet - Show into columns: Location name, Contact person (personal info: image, name, email, phone, position, department) ==> user account, Created time, Creator, Action: Edit, Publish - unpublish, Clone, Del) - List of division in location: division title, contact person: new - Search keyword - Sort column, paging - Google map: show all location in map | 1 | 15 | 2 | 18 |  | 0
1.2. Add location (Improve) | - Location title - Contact person: map with users: add by user ID or username - Add address | 1 | 15 | 1 | 17 |  | 0
1.3. Import/ Export location (Improve) | - Change required import field | 1 | 15 | 1 | 17 |  | 0
1.4. Edit location (improve) | - Edit information in location | 1 | 6 | 1 | 8 |  | 0
1.4. Run location report (Improve) | - Fix show/ hide column feature - Change report field - Fix filter UXD | 1 | 12 | 2 | 15 |  | 0
2. Division |  |  |  |  | 0 |  | 0
2.1. Division list (Improve) | - Division order: Division name anphabet - Location dropdown menu - Show into columns: Division name, Contact person (personal info: image, name, email, phone, position, department) ==> user account, Created time, Creator, Action: Edit, Publish - unpublish, Clone, Del) - List of members/ business unit??? in divison: members, job title ==> add member to division: new - List course of division: course assigned, course requested: new - Search keyword - Sort column - Paging | 2 | 15 | 2 | 19 |  | 0
2.2. Add Division (Improve) | - Division title - Choose location: dropdown list + search by keyword (new) - Contact person: map with users: add by user ID or username (new) - Add address (new) | 1 | 9 | 1 | 11 |  | 0
2.3. Edit division | - Edit information | 1 | 6 | 1 | 8 |  | 0
2.3. Import Division (Improve) | - Change required import field | 1 | 15 | 1 | 17 |  | 0
2.4. Run Division report (Improve) | - Fix show/ hide column feature - Change report field - Fix filter UXD | 1 | 12 | 2 | 15 |  | 0
2.5. Division staff | View list of staff - Users information will roles - Click to user to see user information (course information and progress) ==> Upload image | 2 | 5 | 2 | 9 |  | 0
2.6. Division assigned course | - List of assigned course - List of attendance rate - Project of the course | 3 | 18 | 4 | 25 |  | 0
2.7. Division Requested course | - List of requested course - List of approved course - List of rejected course | 3 | 18 | 4 | 25 |  | 0
3. Business Units??? |  |  |  |  | 0 |  | 0
3.1. Business unit list (Improve) | - Business unit order: Business unit name anphabet - Show into columns: Business unit name, Contact person (personal info: image, name, email, phone, position, department) ==> user account, Created time, Creator, Action: Edit, Publish - unpublish, Clone, Del) - Search keyword - Sort column - Paging | 3 | 22 | 2 | 27 |  | 0
3.2. Add Business unit (Improve) | - Business unit title - Choose Division: dropdown list + search by keyword (new) - Contact person: map with users: add by user ID or username (new) - Add address (new) | 3 | 15 | 2 | 20 |  | 0
3.3. Import Business unit (Improve) | - Change required import field | 3 | 12 | 1 | 16 |  | 0
3.4. Run Business unit report (Improve) | - Fix show/ hide column feature - Change report field - Fix filter UXD | 3 | 6 | 2 | 11 |  | 0
IV. Task to do |  |  |  |  | 0 |  | 0
1. Mark exam |  |  |  |  | 0 |  | 0
1.1. Exam list | - Pending list and marked list - Show by course Show into column: Course image: hover ==> course name, type of exam, trainee name, finished time, Status: mark by ... or not marked, Mark, mark trainee' exam (output) - Action: Edit???, Disable - Enable, Clear mark (only super admin can do this) - Search, filter, sort, paging - Filter: Departments, users, course, status - Export ==> Exam type: System or manual? Assigned for whom? Marked by? | 3 | 18 | 3 | 24 |  | 0
1.2. Mark exam | - Manual mark exam: for exam which do not auto mark/ do not have answer key - Show into column: Course image: hover ==> course name, type of exam, trainee name, finished time, Status: not marked, mark trainee' exam (output) - Action: Mark - Search, filter, sort, paging - Marked => status changed | 3 | 18 | 3 | 24 |  | 0
2. Pending request ==> Request management |  |  |  |  | 0 |  | 0
2.1. Request list (Improve) | - Show into columns: Requesters, Requester's role, Requester postion (Business unit - Division - Location): new, Course's name ==> hover: course info, Request time, Status: Accepted/ Rejected/ Onhold/ Cancelled by .... on ....(time) + Reason | 3 | 18 | 3 | 24 |  | 0
2.2.1. Reject/ Onhold request | - Course info: image, name, public date, requirement (if yes), passing % - Requester info: Image, name, job title - Reason | 1 | 9 | 1 | 11 |  | 0
V. Report | 26 type of reports | 24 | 150 | 20 | 194 |  | 0
VII. Library (filter course theo các major lớn: social science...) | Admin can manage library: add, edit, delete, clone |  |  |  | 0 |  | 0
2.1 List of library | - Order to show the list (anphabet) - How to show: Library ID, Name, Creator, Number of assigned courses, action: View, edit, clone, delete | 2 | 18 | 2 | 22 |  | 0
2.2 Create library | - Library ID - Creator | 2 | 6 | 1 | 9 |  | 0
2.3 View a library | Library detail: - Name, id, creator - List of assigned courses | 2 | 5 | 2 | 9 |  | 0
VIII. Account |  |  |  |  | 0 |  | 0
My account | My account information | 1 | 4 | 1 | 6 |  | 0
Edit account information | edit account information | 1 | 4 | 1 | 6 |  | 0
Change password | Change password | 0.5 | 2 | 0.5 | 3 |  | 0
CMS management | Support guide: list, edit, add, delete | 4 | 18 | 1 | 23 |  | 0
Users contact Management | Users contact form: list, delete | 1 | 18 | 1 | 20 |  | 0
3. Settings (fix) |  |  |  |  | 0 |  | 0
3.1. General info |  | 1 | 5 | 1 | 7 |  | 0
3.2. Theme |  | 1 | 5 | 1 | 7 |  | 0
3.3. Address |  | 1 | 5 | 1 | 7 |  | 0
3.4. Social Media |  | 1 | 4 | 1 | 6 |  | 0
3.5. Other |  | 1 | 9 | 2 | 12 |  | 0
Chat |  | 4 | 27 | 3 | 34 |  | 0
Notification | When user is: - assigned to a course - approved, canceled a request - set a reminder ==> Realtime notification | 4 | 27 | 4 | 35 |  | 0
V/ Integration & System Testing |  |  |  | 24 | 24
VI/ System Deployment |  |  |  |  | 0
Documentation & Guide (PO) | Manual guide, documents, etc | 16 |  |  | 16
Backup, Deployment & Migration (TEAM) |  |  |  |  | 0
TOTAL TECHNICAL DEVELOPMENT EFFORT |  | 187.5 | 994 | 201 | 1382.5 |  | 3208.5
Project Management (PM) | Manage project to accomplish its goals |  |  |  | 207.375 |  | 3208.5
PROJECT TOTAL EFFORT ESTIMATION |  |  |  |  | 1589.875 |  | 6417
Buy theme + fee
* This quote does not include oversea bank transfer fees or currency conversion fees if any which shall be borne by the Client.
TECHNICAL SELECTION
Language: PHP Framework: WordPress Database: MySQL
RESOURCE
* 1 Scrum Master * 1 Product Owner * 1 Designer * 1 Developer
CONSTRAINT/ASSUMPTION
* Client provides all graphic contents including (copyrighted photos, desired color schemes) before project kick-off. * Client to input website content. * Responsive Website running on: * PC: Firefox latest version, Chrome latest version, Safari latest version, IE 9+ * iOS: iPhone 5x, 6.x, iPad 2, 3, 4, Air, iPad mini 1, 2 (iOS 6.x, 7.x, 8.x); (Chrome & Safari latest version) * Android: Phone: 1280 x 720, 1080 x 1920 ; Android tablet: 1280 x 800, 1024 x 600, 1920 x 1080, 2560 x 1600; Operation System: Android 4.x (Chrome & Android Default Browser latest version)

## Trainee View
QSOFT VIETNAM CORPORATION Add: Nbr8 No3 Dich Vong Urban Areas, Cau Giay Dist, Ha Noi, Viet Nam Tel: 84-43-792 5148 Fax: 84-43-792 5147 Email: contact@qsoftvietnam.com Website: http://www.qsoftvietnam.com | [6 empty] | Code: 03e_BM_SA_KD/QSOFT_v1.0 Effective date: 1-Jan-17 Version: v1.0
EFFORT BREAKDOWN AND COST ESTIMATION
Project:
Created by:
Effective:
Validation time: 45 days
Features | Acceptance Criteria | Estimation |  |  |  | Total Effort | Unit Price | Amount
|  | Requirement Development |  | Implementation | Testing | Man-hours
Project initiation | Project environment setup | [6 empty] | 0
- Project planning (PM) | Create project plan | [6 empty] | 0
- Technical Solutioning (TO) | Create Implementation plan & Apply system architecture, starter kit, technical training | [6 empty] | 0
Design
Design | … | [6 empty] | 0
Software development (PO, DEV)
I. My course | [7 empty] | 0
1.1. Course list | View all course: view course general information: image, title, description, author, course index => Request course, Cancel request, Start learining, Continue learning, Reject course + Take the course: Image, Course name, Description, Author, Passing %, Module list, Recent Achievement, Review & Rating, CTA: Start course or Continue course - progress: % finish, Complete ==> view result (date completed, ? attempts, time taken, score. status: pass/ fail, export result: pdf, excel) | 8 |  | 36 | 4 | 48
View the list | - List of assigned course + approved request - List show: Image, title, brief description, duration, start date, end date, assigned or requested by. - show Progress - show status - Paging vs view options - Can search, sort, filter - Show by orders: Newly approved, newly assigned, expire soon
View status | - List of status: + expire soon: mô tả logic + Continue learning: + Newly assigned: + Newly approved requested: + Completed: ok
Search
Sort
Filter
HTML
1.2. Start learning the course | Start learning the course See the details of the course If courses have more than modules => Can users skip module or finish one module is the need to go to next step | 4 |  | 24 | 3 | 31 |  | 0
| Course information |  | 6
| Learning page |  | 9
| Menu functions |  | 6
1.3. Take the quize of the course | Take the quiz of the course Get result and explanation | 2 |  | 9 | 4 | 15 |  | 0
| Quize list |  | 6
| Take the quize |  | 30
Show results
Results page
HTML
1.4. Take exam of the course | - Take the exam of the course - Get answer | 2 |  | 5 | 2 | 9 |  | 0
| Exam information |  | 8
| Exam question list |  | 6
| Take exam |  | 30
Show key
Show results page
15. My exam attempts | Code |  | 8
| HTML |  | 4
| Details attempts HTML |  | 4
| Details attempts code |  | 7
1.5. Retake the exam if any | If fail and the attempt allowed is more than 1 => Retake the exam | 2 |  | 6 | 2 | 10 |  | 0
1.6. Get the certificate | - Complete the exam - Pass the exam - Get the certificate | 2 |  | 6 | 2 | 10 |  | 0
1.7. Open discussion | Open discussion: post topic, comment, tags ==> Not show topic list | 4 |  | 8 | 3 | 15 |  | 0
1.8. Assigned course | View all assigned course: view course general information: image, title, description, author, course index Click to view detail information of the course Click to start learning Can reject the attendance of the course??? Check progress of the course Change status when accept the course and start learning | 4 |  | 18 | 2 | 24 | 103.5 | 2484
1.9. Requested course | View all requested course: view course general information: image, title, description, author, course index List of the requested Course Status of requested course Can view the details of requested course Can cancel the requested course | 4 |  | 6 | 2 | 12 |  | 0
List of requested course
Cancel request
Search, sort, filter
1.10. All courses
List all course
View course details
Course status
Send request
Search, sort, filter
II. Account | [5 empty] | 0 |  | 0
My account | My account information | 1 |  | 4 | 1 | 6 |  | 0
Edit account information | edit account information | 1 |  | 4 | 1 | 6 |  | 0
Change password | Change password | 0.5 |  | 2 | 0.5 | 3 |  | 0
III. My Departments (Department manager) | [5 empty] | 0 |  | 0
1. My Departments information | - View information about my departments | 1 |  | 5 | 1 | 7 |  | 0
2. List of users in the departments | - List of user in the departments - Click to see users details - Click to see assigned course for user - Click to see requested course by users - Click to see user progress | 4 |  | 18 | 4 | 26 |  | 0
2.6. Division assigned course | - List of assigned course - List of attendance rate - Project of the course | 4 |  | 18 | 2 | 24 |  | 0
2.7. Division Requested course | - List of requested course - List of approved course - List of rejected course | 2 |  | 18 | 2 | 22 |  | 0
IV. Dashboard (improve) | - Number of course active, inactive - Number of requested course - History log (last activities, date/time) |  |  |  |  | 0 |  | 0
1. Dashboard (improve) | - Number of course active, inactive - Number of requested course - History log (last activities, date/time) | 4 |  | 15 | 4 | 23 |  | 0
2. My certificate | [5 empty] | 0 |  | 0
2.1 List of certificate (new) | - List of certificate ( Name of course, Name of certificate, button: view, download, print) List created and granted by finishing the course Users can delete the certificated created by themselves only | 1 |  | 5 | 1 | 7 |  | 0
2.2 Add/edit/delete past achievement (improve) | - Course, date, percentage score, certificate image | 2 |  | 5 | 1 | 8 |  | 0
3. My exam attemps | [5 empty] | 0 |  | 0
3.1 Exam progress (new) | - number of exam taken - the improvement in score - rate in class | 2 |  | 5 | 1 | 8 |  | 0
3.2 list of all exam (improve) | - name of course, name of exam, date taken, button view explanation, button view discussion in discussion forum | 2 |  | 5 | 1 | 8 |  | 0
3.3. Finish exam | Show exam info and result (mark + certificate) | 1 |  | 5 | 1 | 7 |  | 0
3.4. Trying exam | Show number of attempts => available attempts remain or time can re-attempt | 2 |  | 5 | 1 | 8 |  | 0
4. Reminders | [5 empty] | 0 |  | 0
4.1 My reminder (improve) | - Filter reminder based on courses and date - Reminder title, description, date, course name - Action: View detail, edit, delete - Share reminder via email or user account: individual or group | 1 |  | 15 | 2 | 18 |  | 0
4,2 Create new reminder (improve) | - Title, description, date, course - Button: Save - Reminder frequency: - Reminder event: dropdown menu - list all the courses - Share reminder via email or user account | 2 |  | 15 | 2 | 19 |  | 0
5. My bookmarks | bookmark video, document, exam, or a discussion thread |  |  |  |  | 0 |  | 0
5.1 List of bookmarks (improve) | course, module, type of bookmarks, action (save, open, delete) | 1 |  | 22 | 1 | 24 |  | 0
6. Account | [5 empty] | 0 |  | 0
6.1 Account information (improve) | * Required fields: - First name, last name, phone, email address - Company, department, title - Country * Optional fields: - Street, city, stat/region, zip code - Facebook, skype, twitter, instagram - Avatar | 0.5 |  | 6 | 0.5 | 7 |  | 0
6.2 Change password | - Current password, new password, confirm password | 0.5 |  | 2 | 0.5 | 3 |  | 0
6.3 Notification settings (improve) | - on/off button for notification - If on, show up all notification options |  |  |  |  | 0 |  | 0
7. Chat | Instant message | 3 |  | 18 | 2 | 23 |  | 0
Contact form |  | 1 |  | 2 | 1 | 4 |  | 0
Notification | Realtime | 4 |  | 23 | 4 | 31 |  | 0
CMS Management |  | 4 |  | 18 | 1 | 23
V/ Integration & System Testing |  |  |  |  | 16 | 16 |  | 0
VI/ System Deployment | [5 empty] | 0
Documentation & Guide (PO) | Manual guide, documents, etc | 16 |  |  |  | 16 |  | 0
Backup, Deployment & Migration (TEAM) | [5 empty] | 0 |  | 0
TOTAL TECHNICAL DEVELOPMENT EFFORT |  | 92.5 |  | 353 | 75.5 | 521 |  | 2484
Project Management (PM) | Manage project to accomplish its goals |  |  |  |  | 78.15 |  | 2484
PROJECT TOTAL EFFORT ESTIMATION | [5 empty] | 599.15 |  | 4968
Buy theme + fee
* This quote does not include oversea bank transfer fees or currency conversion fees if any which shall be borne by the Client.
TECHNICAL SELECTION
Language: PHP Framework: WordPress Database: MySQL
RESOURCE
* 1 Scrum Master * 1 Product Owner * 1 Designer * 1 Developer
CONSTRAINT/ASSUMPTION
* Client provides all graphic contents including (copyrighted photos, desired color schemes) before project kick-off. * Client to input website content. * Responsive Website running on: * PC: Firefox latest version, Chrome latest version, Safari latest version, IE 9+ * iOS: iPhone 5x, 6.x, iPad 2, 3, 4, Air, iPad mini 1, 2 (iOS 6.x, 7.x, 8.x); (Chrome & Safari latest version) * Android: Phone: 1280 x 720, 1080 x 1920 ; Android tablet: 1280 x 800, 1024 x 600, 1920 x 1080, 2560 x 1600; Operation System: Android 4.x (Chrome & Android Default Browser latest version)

## Console
QSOFT VIETNAM CORPORATION Add: Nbr8 No3 Dich Vong Urban Areas, Cau Giay Dist, Ha Noi, Viet Nam Tel: 84-43-792 5148 Fax: 84-43-792 5147 Email: contact@qsoftvietnam.com Website: http://www.qsoftvietnam.com | [5 empty] | Code: 03e_BM_SA_KD/QSOFT_v1.0 Effective date: 1-Jan-17 Version: v1.0
EFFORT BREAKDOWN AND COST ESTIMATION
Project:
Created by:
Effective:
Validation time: 45 days
Features | Acceptance Criteria | Estimation |  |  | Total Effort | Unit Price | Amount
|  | Requirement Development | Implementation | Testing | Man-hours
Project initiation | Project environment setup | [5 empty] | 0
- Project planning (PM) | Create project plan | [5 empty] | 0
- Technical Solutioning (TO) | Create Implementation plan & Apply system architecture, starter kit, technical training | [5 empty] | 0
Design
Design | … | [5 empty] | 0
Software development (PO, DEV)
1. Domain | [6 empty] | 0
1.1. Domain list | Add, Edit, Del, Status change (Active - Deactive), Ressend email, View link | 2 | 18 | 1 | 21 |  | 0
1.2. Add domain | - Sub domain detail - Contact info - Domain setting | 2 | 36 | 1 | 39 |  | 0
2. Dealer |  |  |  |  | 0 |  | 0
2.1. Dealer list | Add, Edit, Del, Status change (Active - Deactive), Ressend email, View link | 2 | 18 | 1 | 21 |  | 0
2.2. Add Dealer | - Sub Dealer detail - Contact info - Allowed course - Dealer setting | 2 | 6 | 1 | 9 |  | 0
3. Email template | - Edit, search, paging, sort | 4 | 18 | 2 | 24 |  | 0
4. Language | Add, edit language | 2 | 18 | 4 | 24 |  | 0
5. Account setting | Name, email, address, phone | 1 | 6 | 1 | 8 |  | 0
V/ Integration & System Testing |  |  |  |  | 0 |  | 0
VI/ System Deployment |  |  |  | 8 | 8
Documentation & Guide (PO) | Manual guide, documents, etc |  |  | 8 | 8 |  | 0
Backup, Deployment & Migration (TEAM) |  |  |  |  | 0 |  | 0
TOTAL TECHNICAL DEVELOPMENT EFFORT |  | 15 | 120 | 27 | 162 |  | 0
Project Management (PM) | Manage project to accomplish its goals |  |  |  | 24.3 |  | 0
PROJECT TOTAL EFFORT ESTIMATION |  |  |  |  | 186.3 |  | 0
Buy theme + fee
* This quote does not include oversea bank transfer fees or currency conversion fees if any which shall be borne by the Client.
TECHNICAL SELECTION
Language: PHP Framework: WordPress Database: MySQL
RESOURCE
* 1 Scrum Master * 1 Product Owner * 1 Designer * 1 Developer
CONSTRAINT/ASSUMPTION
* Client provides all graphic contents including (copyrighted photos, desired color schemes) before project kick-off. * Client to input website content. * Responsive Website running on: * PC: Firefox latest version, Chrome latest version, Safari latest version, IE 9+ * iOS: iPhone 5x, 6.x, iPad 2, 3, 4, Air, iPad mini 1, 2 (iOS 6.x, 7.x, 8.x); (Chrome & Safari latest version) * Android: Phone: 1280 x 720, 1080 x 1920 ; Android tablet: 1280 x 800, 1024 x 600, 1920 x 1080, 2560 x 1600; Operation System: Android 4.x (Chrome & Android Default Browser latest version)